## Feuil1
ETU1844 | RAMANANTSALAMA Dirk Tony
Catégorie | Taches | Type | Qui | Estimation | Temps passé | Reste à faire | Avancement
Debut | Mise en place de l’environment | Rust + Svelte | Tony | 60 | 60 | 0 | 100%
Concetions | Conception front-end | Excalidraw | Tony | 15 | 15 | 0 | 100%
Concetions | MCD | MCD | Tony | 15 | 15 | 0 | 100%
Base de donnee | Migration reset | SQL | Tony | 5 | 5 | 0 | 100%
Base de donnee | Migration create_client | SQL | Tony | 5 | 5 | 0 | 100%
Base de donnee | migration create_unite | SQL | Tony | 5 | 5 | 0 | 100%
Base de donnee | Migration create_finition | SQL | Tony | 5 | 5 | 0 | 100%
Base de donnee | Migraton create_materiels | SQL | Tony | 5 | 5 | 0 | 100%
Base de donnee | Migration create_type_chantier | SQL | Tony | 5 | 5 | 0 | 100%
Base de donnee | Migration create_devis | SQL | Tony | 5 | 5 | 0 | 100%
Base de donnee | Migration create_chantier | SQL | Tony | 5 | 5 | 0 | 100%
Base de donnee | Migration v_materiel_unite | SQL | Tony | 5 | 5 | 0 | 100%
Base de donnee | Migration v_devis_materiel | SQL | Tony | 5 | 5 | 0 | 100%
Base de donnee | Migration v_chantier_finition | SQL | Tony | 5 | 5 | 0 | 100%
Backend | Function reset database | Rust | Tony | 15 | 30 | 0 | 100%
Backend Conception | Modele Chantier | Rust | Tony | 10 | 30 | 0 | 100%
Backend Conception | Modele client | Rust | Tony | 10 | 5 | 0 | 100%
Backend Conception | Modele devis | Rust | Tony | 10 | 5 | 0 | 100%
Backend Conception | Modele finition | Rust | Tony | 10 | 5 | 0 | 100%
Backend Conception | Modele materiel | Rust | Tony | 10 | 5 | 0 | 100%
Backend Conception | Modele type_chantier | Rust | Tony | 10 | 5 | 0 | 100%
Backend Conception | Modele unite | Rust | Tony | 10 | 5 | 0 | 100%
Backend Conception | Modele v_chantier_finition | Rust | Tony | 10 | 5 | 0 | 100%
Backend Conception | Modele v_devis_materiel | Rust | Tony | 10 | 5 | 0 | 100%
Backend GraphQL | Front-Office Graphql Schema | Rust | Tony | 20 | 20 | 0 | 100%
Backend GraphQL | Admin GraphQL Schema | Rust | Tony | 20 | 20 | 0 | 100%
Front-office backend | Client login | Rust | Tony | 20 | 15 | 0 | 100%
Front-office backend | list chantier client | Rust | Tony | 20 | 5 | 0 | 100%
Front-office backend | creation chantier client | Rust | Tony | 20 | 0 | 20 | 0%
Front-office backend | payement client | Rust | Tony | 15 | 0 | 15 | 0%
Admin backend | Upsert AdminClient | Rust | Tony | 15 | 15 | 0 | 100%
Admin backend | Upsert AdminChantier | Rust | Tony | 5 | 5 | 0 | 100%
Admin backend | Upsert AdminDevis | Rust | Tony | 5 | 5 | 0 | 100%
Admin backend | Upsert AdminFinition | Rust | Tony | 5 | 5 | 0 | 100%
Admin backend | Upsert AdminMateriels | Rust | Tony | 5 | 5 | 0 | 100%
Admin backend | Upsert AdminTypeChantier | Rust | Tony | 5 | 5 | 0 | 100%
Admin backend | Upsert AdminUnite | Rust | Tony | 5 | 5 | 0 | 100%
Admin backend | Upsert Payement | Rust | Tony | 5 | 5 | 0 | 100%
Admin backend | Admin ClientQueries | Rust | Tony | 5 | 0 | 5 | 0%
Admin backend | Admin ChantierQueries | Rust | Tony | 5 | 0 | 5 | 0%
Admin backend | Admin DevisQueries | Rust | Tony | 5 | 0 | 5 | 0%
Admin backend | Admin MaterielsQueries | Rust | Tony | 5 | 0 | 5 | 0%
Admin backend | Admin TypeChantier Queries | Rust | Tony | 5 |  | 5 | 0%
Admin backend | Admin Unite Queries | Rust | Tony | 5 |  | 5 | 0%
Admin backend | Admin Payement Queries | Rust | Tony | 5 |  | 5 | 0%
Frontend client | Page Login | Svelte | Tony | 10 |  | 10 | 0%
Frontend client | Liste chantier | Svelte | Tony | 10 |  | 10 | 0%
Frontend client | Export devis | Svelte | Tony | 15 |  | 15 | 0%
Frontend client | Creation chantier | Svelte | Tony | 10 |  | 10 | 0%
Frontend client | Validation devis | Svelte | Tony | 15 |  | 15 | 0%
Frontend client | Validation payement | Svelte | Tony | 15 |  | 15 | 0%
Frontend Admin | Login | Svelte | Tony | 10 |  | 10 | 0%
Frontend Admin | Tableau de bord layout | Svelte | Tony | 10 |  | 10 | 0%
Frontend Admin | Montant total des devis | Svelte | Tony | 5 |  | 5 | 0%
Frontend Admin | Listes des devis | Svelte | Tony | 10 |  | 10 | 0%
Frontend Admin | Fiche devis | Svelte | Tony | 10 |  | 10 | 0%
Frontend Admin | import maison et travaux | Svelte | Tony | 15 |  | 15 | 0%
Frontend Admin | import paiement | Svelte | Tony | 15 |  | 15 | 0%
Frontend Admin | Paiment total | Svelte | Tony | 15 |  | 15 | 0%
|  |  |  | 615 | 355 | 235 | 60.17%
Repo Git | https://github.com/tonymushah/evaluation-stage-mai-2023.git
Estimation: | 615
Temps passé | 355
Reste à faire | 235

## Feuille2
*Valeur en Minutes